## General
Created by: Lejla Musanovic
Approved by: ABH Management Team

## Test Plan
Test Plan Strategy
Name of Project or Application
PlaceLab (https://demo.placelab.com/)
Type of Computing Environments
Web-based
Introduction
The testing of PlaceLab module Roads will focus on verifying the functionality of creating Road Analysis report. Road Analysis is a tool that analyses data to find roads from starting point to end point. User passes data as coordinates in a file that is going to be uploaded for analysing. PlaceLab uses Google and Bing to analyse and find the road from their databases.
Objectives
The goal of this testing is to verify the functionality of Road Analysis. After the testing is completed it should be determined: - that only correct type of uploaded file will result in report creation - that deleting report is possible
Scope of Testing
Testing of Roads module will include the following: - creation of Road Analysis report - validation of created report widgets - deleting created report
Environment Requirements
Windows 10 Chrome Version 114.0.5735.91 Edge Version 113.0.1774.57 .txt file editor
Test Schedule
In order to finish the testing of Road Analysis, it is given a seven days period from 29.05.2023. to 04.06.2023. Testing is planned to following schedule: - 29.05.2023. and 30.05.2023. - Test planning and preparation - from 31.05.2023. to 03.06.2023. - Test case design, Test execution, Bug tracking, Enhancement tickets creation - 04.06.2023 - Test reporting and Conclusion
Features (not) to be Tested
Feature to be tested: Module: ROADS - Road Analysis
Resources and Responsibilities
Test planning and testing will be performed by QA Lejla Musanovic
Dependency
Google Maps (https://www.google.com/maps) Bing Maps (https://www.bing.com/maps/)
Risks
The following is the list of possible risks: - The https://demo.placelab.com web application is down. - The Google Maps and Bing Maps are down. - QA has a internet connection issue. - Less time for testing. - Account credit has been spent.
Approvals

## Test Scenarios
Project Name | PlaceLab Module Roads
Created By | Lejla Musanovic
Creation Date | 29.05.2023.
Reviewed By
Reviewed Date
Test Scenario ID | Test cases IDs in Test Scenario | Test Scenario Description | Number of Test Cases Written | Number of Test Cases Executed | Number of Test Cases Passed | Number of Test Cases Failed
TS_001 | TC_001 - TC_013 | Creating the Roads Analysis Report | 13 | 13 | 10 | 3
TS_002 | TC_014 - TC_016 | Validating pre-created Roads report | 3 | 3 | 3 | 0
TS_003 | TC_017 | Deleting created Roads Report from the queries list | 1 | 1 | 1 | 0

## Test Cases
Test Case ID | Test Scenario ID | Test Case Title | Pre-requisites | Test Steps | Expected Results | Actual Results | Priority | Pass/Fail | Comments
TC_001 | TS_001 | Validate creating the Road Analysis Report with .txt sample file using Browse button | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report .txt sample file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the pre-downloaded .txt sample file and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 7. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 8. Create Report button is clickable 9. The user is redirected to the Please wait while we analyze your file page 10. The user is redirected to the Reports page 11. The Road Analysis report is successfuly created | As expected | High | Pass
TC_002 | TS_001 | Validate creating the Road Analysis Report with .txt sample file using the dragging method | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report sample file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Drag the pre-downloaded .txt sample file from your PCs file explorer and drop it on Create Road Analysis Report form 2. Wait until file is successfuly uploaded and Status: Created is shown 3. Check if the Enter Report Name field is filled in with sample file's name 4. Click on the Create Report button 5. Click on Hide this screen and go to reports link 6. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. The sample file has been uploaded 2. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 3. Enter Report Name field is filled in with the sample file name 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 6. Create Report button is clickable 7. The user is redirected to the Please wait while we analyze your file page 8. The user is redirected to the Reports page 9. The Road Analysis report is successfuly created | As expected | High | Pass
TC_003 | TS_001 | Validate creating the Road Analysis Report with .csv sample file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report .csv sample file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the .csv sample file and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 7. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 8. Create Report button is clickable 9. The user is redirected to the Please wait while we analyze your file page 10. The user is redirected to the Reports page 11. The Road Analysis report is successfuly created | As expected | High | Pass
TC_004 | TS_001 | Validate creating the Road Analysis Report with .wkt sample file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report .wkt sample file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the .wkt sample file and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 7. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 8. Create Report button is clickable 9. The user is redirected to the Please wait while we analyze your file page 10. The user is redirected to the Reports page 11. The Road Analysis report is successfuly created | As expected | High | Pass
TC_005 | TS_001 | Validate creating the Road Analysis Report with .zip sample file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report .zip sample file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the .zip sample file and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 7. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 8. Create Report button is clickable 9. The user is redirected to the Please wait while we analyze your file page 10. The user is redirected to the Reports page 11. The Road Analysis report is successfuly created | As expected | High | Pass
TC_006 | TS_001 | Validate creating the Road Analysis Report with only a mandatory column (THE_GEOM) | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file that contains only a mandatory (THE_GEOM) column is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that contains only a mandatory (THE_GEOM) column and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The file is uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 6. The notification message is present above Create Report button 7. Create Report button is clickable 8. The user is redirected to the Please wait while we analyze your file page 9. The user is redirected to the Reports page 10. The Road Analysis report is successfuly created | 1. Pop-up window for file exploring has appeared 2. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 3. The sample file has been uploaded and Status: Completed is shown 4. Enter Report Name field is filled in with the sample file name 5. The message File contains only one column. ID column is missing, please double check input file. is displayed 6. Create Report button is clickable 7. The user is redirected to the Please wait while we analyze your file page 8. The user is redirected to the Reports page 9. The Road Analysis report is successfuly created | High | Fail | Bug_001
TC_007 | TS_001 | Validate creating the Road Analysis Report with two roads | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report sample file with two roads is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the pre-downloaded .txt sample file and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 7. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 8. Create Report button is clickable 9. The user is redirected to the Please wait while we analyze your file page 10. The user is redirected to the Reports page 11. The Road Analysis report is successfuly created | As expected | High | Pass
TC_008 | TS_001 | Try to create Road Analysis Report with the empty file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The empty file is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the sample file and try to upload it 3. Check if the file is uploaded 4. Check if File is empty. message appeared 5. Try to click on Create Report button 6. Click on Reports from navigation bar | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message File is empty. is shown above Create Report button 4. Create Report button is unclickable 5. Report is not created and is not diplayed on the Reports page | As expected |  | Pass
TC_009 | TS_001 | Try to create Road Analysis Report with no data in mandatory (THE_GEOM) column | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file with no data in mandatory (THE_GEOM) column is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file with no data in mandatory (THE_GEOM) column and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report appears on Reports page 8. Check if the status is Invalid file which indicates that report is not created 8. Try to click on the report name to open report | 1. Pop-up window for file exploring has appeared 2. The sample file has been uploaded and Status: Completed is shown 3. Enter Report Name field is filled in with the sample file name 4. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 5. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 6. The message Delimiter ¦ is recognized. All needed headers are present. is present above Create Report button 7. Create Report button is clickable 8. The user is redirected to the Please wait while we analyze your file page 9. The user is redirected to the Reports page 10. The Road Analysis report is not created and status is Invalid file 11. User cannot click on the report and it can not be opened | As expected |  | Pass
TC_010 | TS_001 | Try to create Road Analysis Report without mandatory (THE_GEOM) column data and header in the file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file that does not contain mandatory (THE_GEOM) header and data is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain mandatory (THE_GEOM) column and upload it 3. Wait until the alert message Mandatory header(s) missing: THE_GEOM is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Mandatory header(s) missing: THE_GEOM is shown above Create Report button 4. Create Report button is unclickable 5. Report is not created and is not diplayed on the Reports page | As expected | Medium | Pass
TC_011 | TS_001 | Try to create Road Analysis Report without headers in the file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file without headers is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain headers and upload it 3. Wait until the alert message Header(s) missing: ID, STREET, THE_GEOM. is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Header(s) missing: ID, STREET, THE_GEOM. is shown above Create Report button 4. Create Report button is unclickable | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message File contains only header. is shown above Create Report button 4. Create Report button is unclickable | High | Fail | Bug_002
TC_012 | TS_001 | Try to create Road Analysis Report without mandatory (THE_GEOM) header in the file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file without mandatory (THE_GEOM) header is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain headers and upload it 3. Wait until the alert message Mandatory header(s) missing: THE_GEOM. is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Mandatory header(s) missing: THE_GEOM is shown above Create Report button 4. Create Report button is unclickable | As expected | Medium | Pass
TC_013 | TS_001 | Try to create Road Analysis Report without ID and STREET headers in the file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The file without ID and STREET headers is ready to be used and uploaded The user has navigated to the Create Road Analysis Report form from the home page by clicking on the Create Report dropdown menu and then clicking on the Road Analysis | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain headers and upload it 3. Wait until the alert message Header(s) missing: ID, STREET. is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Mandatory header(s) missing: ID, STREET is shown above Create Report button 4. Create Report button is unclickable | 1. Pop-up window for file exploring has appeared 2. The sample file is running 3. Status Running is shown 4. The message Delimiter is not recognized. Please, provide one. is shown above Create Report button 5. Delimiter field for providing delimiter is displayed 6. After providing delimiter by entering it in delimiter field and clicking on Try this one button, the alert message File could not be parsed using the delimiter you provided: ¦. is displayed. 7. After a five attempts the file is still running | Medium | Fail | Bug_003
TC_014 | TS_002 | Validate the result page of created Road Analysis Report with sample file | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report is created with sample file | 1. Click on the previously created Road Analysis report to open it 2. Validate that file name is the same as previously provided during the creation of report 3. Validate that Analysis info table is displayed and it contains all data 4. Validate that Map is displayed 5. Validate that Road status statistics are displayed 6. Validate that Route status statistics for Google and Bing are displayed 7. Validate that Road name status is diaplayed 8. Validate that Navigable roads is displayed 9. Validate that Direction of travel is displayed 10. Validate that Roads with Reverse Orientation is displayed 11. Validate that Road Status (Pedestrian Mode) is displayed 12. Validate that Navigable roads is displayed | 1. Report is opened 2. File name is the same as previously provided during the creation of report 3. Analysis info table is displayed and it contains all data 4. Map is displayed 5. Road status statistics are displayed 6. Route status statistics for Google and Bing are displayed 7. Road name status is diaplayed 8. Navigable roads is displayed 9. Direction of travel is displayed 10. Roads with Reverse Orientation is displayed 11. Road Status (Pedestrian Mode) is displayed 12. Navigable roads is displayed | As expected | High | Pass
TC_015 | TS_002 | Validate the Analysis info table on created report page | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report is created with sample file The user is on the created report results page | 1. Validate that Analysis info table is displayed and it contains all data 2. Hover the … button within the table to check if Add/Edit conclusion, Copy link and Remove widget options are displayed. 3. Click on the Add/Edit conclusion 4. Add text in Summary 5. Click on Save button 6. Click on copy link 7. Open it in the new tab to validate that is copied 8. Click on Remove widget 9. On the pop-up window Are you sure you want to delete this widget? confirm with OK | 1. Analysis info table is displayed and it contains all data 2. All options are displayed 3. Summary is opened 4. Text is added and it appears within the table 5. Link is copied 6. The Analysis info widget is removed from the page | As expected | High | Pass
TC_016 | TS_002 | Validate the Map on created report page | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in and has enough credits for creating reports The report is created with sample file The user is on the created report results page | 1. Validate that Map is displayed 2. Hover the … button within the table to check if Add/Edit conclusion, Copy link and Remove widget options are displayed. 3. Click on the Add/Edit conclusion 4. Add text in Summary 5. Click on Save button 6. Click on copy link 7. Open it in the new tab to validate that is copied 8. Click on Remove widget 9. On the pop-up window Are you sure you want to delete this widget? confirm with OK | 1. Map is displayed and it contains all data 2. All options are displayed 3. Summary is opened 4. Text is added and it appears within the table 5. Link is copied 6. The Analysis info widget is removed from the page | As expected | High | Pass
TC_017 | TS_003 | Validate that report can be deleted from Reports page | The PlaceLab application (https://demo.placelab.com/) is opened in the browser The user has valid credentials to log in and access to the Road Analysis feature The user is logged in The report is previously created with sample file The user is on Reports page | 1. Click on the checkbox of the previously created report in the second column of Reports table 2. Click on the bin icon on top of the right corner of Reports table 3. Click on Confirm button in Confirm Delete window 4. Validate the Successfully deleted selected queries notification message 5. Check if selected report is deleted and not displayed on Reports list | 1. Checkbox is marked 2. Pop-up window Confirm Delete appeared 3. Confirm button is clickable 4. Confirm Delete window disappeared 5. Notification message Successfully deleted selected queries is displayed on Reports page 4. The report is deleted | As expected | High | Pass

## Bug Report
ID Number | Reporter | Submit Date | Description | Steps to reproduce | Expected Result | Actual Result | Screenshot | Environment | Severity | Priority | Assigned to
Bug_001 | Lejla | 03.06.2023. | When the user is creating Road Analysis report with file that contains only mandatory (THE_GEOM) column, the message File contains only one column. ID column is missing, please double check input file. is displayed even though the ID column is not mandatory. | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that contains only a mandatory (THE_GEOM) header and upload it 3. Wait until file is successfuly uploaded and Status: Created is shown 4. Check if the Enter Report Name field is filled in with sample file's name 5. Click on the Create Report button 6. Click on Hide this screen and go to reports link 7. Wait until the report is created and it appears on Reports page with OK status which indicates that report has been successfuly created 8. Click on the report name link to redirect to the report results page | 1. Pop-up window for file exploring has appeared 2. The file is uploaded 3. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 4. Status Created showed up on the left side of the uploading progress bar after the sample file is successfully uploaded and green check mark is displayed on the right side of the progress bar 5. Enter Report Name field is filled in with the sample file name 6. The notification message is present above Create Report button 7. Create Report button is clickable 8. The user is redirected to the Please wait while we analyze your file page 9. The user is redirected to the Reports page 10. The Road Analysis report is successfuly created | 1. Pop-up window for file exploring has appeared 2. Please wait while we analyze your file message is displayed while waiting the sample file to be uploaded 3. The sample file has been uploaded and Status: Completed is shown 4. Enter Report Name field is filled in with the sample file name 5. The message File contains only one column. ID column is missing, please double check input file. is displayed 6. Create Report button is clickable 7. The user is redirected to the Please wait while we analyze your file page 8. The user is redirected to the Reports page 9. The Road Analysis report is successfuly created |  | Windows 10, Chrome Version 114.0.5735.91 Edge Version 113.0.1774.57 | Minor | Low
Bug_002 | Lejla | 03.06.2023. | After trying to upload the sample file without headers the message File contains only header. is shown above Create Report button even though the headers are missing in the file. | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain headers and upload it 3. Wait until the alert message Header(s) missing: ID, STREET, THE_GEOM. is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Header(s) missing: ID, STREET, THE_GEOM. is shown above Create Report button 4. Create Report button is unclickable 5. Report is not created and is not diplayed on the Reports page | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message File contains only header. is shown above Create Report button 4. Create Report button is unclickable 5. Report is not created and is not diplayed on the Reports page |  | Windows 10, Chrome Version 114.0.5735.91 Edge Version 113.0.1774.57 | Minor | Low
Bug_003 | Lejla | 03.06.2023. | When the user is trying to upload the sample file where the first row is ¦THE_GEOM header and in the second row are provided data for ID, STREET and THE_GEOM, the file starts uploading but then message Delimiter is not recognized. Please, provide one. shows up. After five attemts of trying to provide delimiter, file is still running and alert message is changed to File could not be parsed using the delimiter you provided: ¦. | 1. Click on the Browse button on the Create Road Analysis page 2. Choose the file that does not contain headers and upload it 3. Wait until the alert message Header(s) missing: ID, STREET. is shown | 1. Pop-up window for file exploring has appeared 2. The sample file is not uploaded 3. The message Mandatory header(s) missing: ID, STREET is shown above Create Report button 4. Create Report button is unclickable | 1. Pop-up window for file exploring has appeared 2. The sample file is running 3. Status Running is shown 4. The message Delimiter is not recognized. Please, provide one. is shown above Create Report button 5. Delimiter field for providing delimiter is displayed 6. After providing delimiter by entering it in delimiter field and clicking on Try this one button, the alert message File could not be parsed using the delimiter you provided: ¦. is displayed. 7. After a five attempts the file is still running |  | Windows 10, Chrome Version 114.0.5735.91 Edge Version 113.0.1774.57 | Moderate | Medium

## Enhancement
ID | Feature name | Current State | Future State
Improvement_01 | Providing coordinates that will be analysed | On the Create Road Analysis page as a tutorial message stays that file should be uploaded with geometry specified as longitude latitude and data is analysed in that order. | The tutorial message should be changed and in the file should be provided and analysed with latitude first because it is a convention of providing geometry coordinates.
Improvement_02 | Login | When a user is entering a password in the password field on login page, there is no unseen option that would provide to the user to check if password is entered correctly. | The login page should have unseen method for checking if password is correctly entered.
Improvement_03 | Detailed Data of created Road Analysis report | If report contain only one road length filter within Detailed data has no function. | The length filter for one road report is removed.
Improvement_04 | Road Analysis Methodology | In Google API Road Analysis Methodology is written "we use two modes for a search: drawing and walking". | In Google API Road Analysis Methodology should be written "we use two modes for a search: driving and walking".